## Sheet1
| Features | Initial Estimate | Adjust Factor | Adjust Estimate | Stage: | 1 | 2 | 3
M3-1 | Welcome Page with Login/Register Buttons | 6 | 0.3 | 7.8
M3-2 | Login Screen | 6 | 0.3 | 7.8
M3-3 | Login button transitions to login screen | 6 | 0.3 | 7.8
M4-1 | Login Handling through Login Screen | 6 | 0.3 | 7.8
M5-1 | Registration Screen | 6 | 0.3 | 7.8
M5-2 | Registration Handling | 6 | 0.3 | 7.8
M6-1 | Home Page Screen with Appropirate Buttons | 4 | 0.3 | 5.2
M6-2 | New Account Creation Screen | 4 | 0.3 | 5.2
M6-3 | New Account Creation Handling | 8 | 0.3 | 10.4
M7-1 | Account Selection Screen | 3 | 0.3 | 3.9
M7-2 | Account Balance Screen | 4 | 0.3 | 5.2
M7-3 | New Transaction Screen with Appropriate Fields | 4 | 0.3 | 5.2
M7-4 | New Transaction Handling | 8 | 0.3 | 10.4
M8-1 | Spending Category Report Promt Screen | 6 | 0.3 | 7.8
M8-2 | Spending Category Report Screen | 4 | 0.3 | 5.2
M9-1 | Save/Loading Application | 4 | 0.3 | 5.2
M9-2 | Local Information Storage | 8 | 0.3 | 10.4
M10 | Code Documentations | 4 | 0.3 | 5.2
Total |  | 97 | 0.3 | 126.1 |  | 0 | 0 | 0