## Sheet1
Tasks | Responsible | Status | 1 | 2 | 3 | 4 | Team Members
Set up Repository on Github | David | Completed | 0 |  |  |  | Ben
Set up Project for M2 on Github | David | Completed | 0 |  |  |  | Casey
Edit and Commit Files for M2 | Everyone | In Progress | 1 |  |  |  | David
Install and Set up Gradle | Everyone | In Progress | 1 |  |  |  | Inseok
Adding/Removing/Buidling Files for M2 | Everyone | In Progress | 1 |  |  |  | Matthew
|  |  | 3 | 0 | 0 | 0 | Everyone
Get 10 Use Cases Done | Project Leader | Not Started | 4 |  |  |  | Project Leader
Project creates/loads on a device/emulator | Ben | Not Started | 4
Welcome Screen with Login/Register Buttons | Casey | Not Started | 4 |  |  |  | Status
Login Screen/Display with appropriate fields | Inseok | Not Started | 4 |  |  |  | Not Started
|  |  | 16 | 0 | 0 | 0 | In Progress
Prepare UML Domain Models | Project Leader | Not Started | 6 |  |  |  | Completed
Create Classes to store Login information | David | Not Started | 4
Create Classes to handle Login information | David | Not Started | 4
|  |  | 14 | 0 | 0 | 0